## Task Estimation
Sprint No. | Product Backlog Items | DOD ของแต่ละ item | Sprint Tasks | Initial Estimate of Effort | New Estimate of Effort Remaining at The End of Day… | [7 empty] | * ตัวเลข Effort ในตารางตัวสีแดงเป็น ค่าที่ Estimate ให้เป็นไปตาม Ideal เท่านั้น ยังไม่ได้ลงมือทำจริงๆ
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Actual Effort
1 | Approved Requirements Baseline | Requirement document approved | Requirement workshop / interview | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
|  |  | Requirement analysis & clarification | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0 |  |  |  | sum
|  |  | Write Functional Requirement Spec | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 |  |  | sprint 1 | 56
|  |  | Review & sign-off (PO / Stakeholder) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 |  |  | sprint 2 | 28
|  |  | Requirement document (baseline) | 12 | 9 | 6 | 6 | 6 | 6 | 3 | 0 |  |  | sprint 3 | 24
2 | Defined MVP Scope | Scope document approved | Define MVP scope | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 |  |  | sprint 4 | 24
|  |  | Identify out-of-scope & assumptions | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 |  |  | sprint 5 | 40
|  |  | Scope document | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 |  |  | sprint 6 | 56
3 | User Flow Definition | User flow diagram approved | Draft user flow diagram | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 |  |  | sprint 7 | 122
|  |  | Review with PO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 |  |  | sprint 8 | 130
|  |  | Final user flow document | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 |  |  | sprint 9 | 132
4 | Data Mapping Specification | Data mapping document approved | Identify entities & sources | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 |  |  | sprint 10 | 72
|  |  | Data mapping document | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 |  |  | sprint 11 | 100
5 | High-level System Architecture | Architecture document approved | Define system components | 12 | 12 | 12 | 12 | 9 | 6 | 3 | 0 |  |  | sprint 12 | 104
|  |  | Architecture diagrams | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 |  |  | sprint 13 | 96
|  |  | Review & approval | 24 | 18 | 12 | 6 | 0 | 0 | 0 | 0 |  |  | sprint 14 | 80
6 | UI/UX Design Package | UI spec approved | Wireframe | 24 | 24 | 24 | 24 | 18 | 12 | 6 | 0 |  |  | sprint 15 | 92
|  |  | High-fidelity UI | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 |  |  | sprint 16 | 50
|  |  | UX review & iteration | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | UI specification | 20 | 15 | 10 | 5 | 0 | 0 | 0 | 0 |  |  | sum all | 1206
7 | Authentication API | Code implemented & deployed Unit + Integration test passed Security test passed UAT approved API doc & test report completed | Implement login / logout endpoint | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0
|  |  | Token generation & validation (JWT / SSO) | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0
|  |  | Role & access control check | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
|  |  | Standard error response | 18 | 18 | 18 | 18 | 18 | 12 | 6 | 0
|  |  | Unit test: auth service, token logic | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Integration test: login ร่วมกับ protected API | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Security test: authz, token expiry, invalid token | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | UAT | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | API documentation (Swagger) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Test report | 24 | 18 | 12 | 6 | 0 | 0 | 0 | 0
8 | Subject & Exam Schedule API | Code + executable API Unit & Integration test passed Performance & security test passed UAT approved API doc & test report completed | Implement subject search API | 24 | 18 | 12 | 6 | 0 | 0 | 0 | 0
|  |  | Implement exam schedule query | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  |  | Custom filter (code, name, section, instructor, year, term) | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
|  |  | Error & empty response handling | 18 | 18 | 18 | 18 | 18 | 12 | 6 | 0
|  |  | Unit test: service & repository | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Integration test: API + database | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Performance test: load & response time | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Security test: input validation, authz | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | UAT | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | API documentation (Swagger) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Test report | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
9 | Public Subject Search UI | UI implemented & integrated Unit + Integration test passed UAT approved Responsive verified User manual & test report updated | Setup frontend route & state management | 24 | 18 | 12 | 6 | 0 | 0 | 0 | 0
|  |  | Search form (รหัสวิชา, ชื่อวิชา, section, อาจารย์, ปี/เทอม) | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  |  | Subject list & pagination | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
|  |  | Error / empty state handling | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  |  | API integration (REG-3) | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Responsive UI (mobile / tablet) | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Unit test: search form, list component | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Integration test: search ร่วมกับ result flow | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | UAT: search scenario ตาม requirement | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | Update user manual (public search) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Test report | 20 | 15 | 10 | 5 | 0 | 0 | 0 | 0
10 | Exam Detail Page | UI implemented & integrated Unit + Integration test passed UAT approved Document updated | Exam detail UI | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
|  |  | API integration | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
|  |  | Error handling (no exam / invalid subject) | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
|  |  | Unit test: detail component | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Integration test: list ร่วมกับ detail flow | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | UAT | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | User manual update | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Test report | 24 | 18 | 12 | 6 | 0 | 0 | 0 | 0
11 | Authentication UI & Route Guard | Auth UI implemented Security & integration test passed UAT approved Document updated | Login / logout page | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
|  |  | Token handling | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  |  | Auth guard (protected route) | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
|  |  | Error state (invalid credential / expired token) | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Unit test: auth components | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
|  |  | Integration test: login กับหน้า protected page | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Security test: route access control | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | UAT | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | User manual (login flow) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Test report | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0
12 | Student Exam Dashboard | UI implemented & integrated Unit + Integration test passed UAT approved Performance acceptable Document updated | Student profile section | 28 | 21 | 14 | 7 | 0 | 0 | 0 | 0
|  |  | Exam calendar UI | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0
|  |  | API integration | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
|  |  | Empty / error state | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Unit test: calendar & profile components | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Integration test: login กับหน้า dashboard | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | UAT | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Performance check (render ปฏิทิน) | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | User manual (dashboard) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Test report | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
13 | CI/CD Pipeline | CI pipeline running automatically All automated tests executed in pipeline Successful deploy to staging CI/CD document & report completed | Define CI/CD workflow (branch, trigger) | 24 | 18 | 12 | 6 | 0 | 0 | 0 | 0
|  |  | Configure build pipeline (frontend + backend) | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  |  | Integrate unit & integration test into pipeline | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
|  |  | Artifact management | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Staging deployment automation | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Pipeline dry-run test | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Failure / rollback scenario test | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | CI/CD configuration document | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Pipeline execution report | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
14 | System Verification & UAT | Smoke test passed UAT approved by stakeholder No critical defect open Test report completed | Define smoke test scenarios | 12 | 12 | 6 | 0 | 0 | 0 | 0 | 0
|  |  | Execute smoke test (staging) | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
|  |  | Prepare UAT test cases | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  |  | Execute UAT with stakeholders | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Defect tracking & retest | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | Smoke test | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | UAT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | UAT report | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Defect summary | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0
15 | System Hardening & Bug Fix | No critical / high severity bugs Regression test passed Fix report completed | Analyze reported defects | 28 | 28 | 21 | 14 | 7 | 0 | 0 | 0
|  |  | Fix functional & UI bugs | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
|  |  | Regression testing | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Verify fixes in staging | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Regression test | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Targeted retest | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Bug fix summary | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  | Regression test report | 20 | 15 | 10 | 5 | 0 | 0 | 0 | 0
16 | Final Documentation Package | All documents reviewed & approved Ready for system handover | Finalize user manual (all features) | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
|  |  | Consolidate test reports (Unit, Int, UAT, Perf, Sec) | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
|  |  | Deployment & configuration guide | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
|  |  | Documentation review | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | User manual | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | Consolidated test report | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  |  | Deployment guide | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0

## Evolved Task Board
Backlog | Story | Tasks |  |  |  | Coding | Testing | Approval | Done
| As a student, I want to check on my final exam dates so that I can plan ahead. | No.1 Approved Requirements Baseline (56 Hours) | No.2 Defined MVP Scope (28 Hours) | No.3 User Flow Definition (24 Hours) | No.4 Data Mapping Specification (24 Hours)
[10 empty] | Item | Hours
[10 empty] | Approved Requirements Baseline | 56
[10 empty] | Defined MVP Scope | 28
[10 empty] | User Flow Definition () | 24
[10 empty] | Data Mapping Specification | 24
[10 empty] | High-level System Architecture | 40
[10 empty] | UI/UX Design Package | 56
[10 empty] | Authentication API | 122
[10 empty] | Subject & Exam Schedule API | 130
[10 empty] | Public Subject Search UI | 132
|  | No.5 High-level System Architecture (40 Hours) | No.6 UI/UX Design Package (56 Hours) | No.7 Authentication API (122 Hours) | No.8 Subject & Exam Schedule API (130 Hours) |  |  |  |  | Exam Detail Page | 72
[10 empty] | Authentication UI & Route Guard | 100
[10 empty] | Student Exam Dashboard | 104
[10 empty] | CI/CD Pipeline | 96
[10 empty] | System Verification & UAT | 80
[10 empty] | System Hardening & Bug Fix | 92
[10 empty] | Final Documentation Package | 50
|  | No.9 Public Subject Search UI (132 Hours) | No.10 Exam Detail Page (72 Hours) | No.11 Authentication UI & Route Guard (100 Hours) | No.12 Student Exam Dashboard (104 Hours)
|  | No.13 CI/CD Pipeline (96 Hours) | No.14 System Verification & UAT (80 Hours) | No.15 System Hardening & Bug Fix (92 Hours) | No.16 Final Documentation Package (50 Hours)